## Slide 1: PUSD Reading Intervention Plan Read 180 and System 44 Implementation Plan
August 5,2014
Notes: Purpose of the presentation today is to give you an overview of the Reading Intervention plan for all students beginning this fall
As you may recall, there were concerns expressed by the special education providers serving general education students in the Read 180 program in relation to the impact on the special education caseload. As intervention is key component of Goal 1 (1.3), it was determined the program would be made available to students grades 4 through 12 with intensive reading needs district wide.

## Slide 2: Program is an Intervention in the areas of:
Decoding Skills
Vocabulary
Comprehension
Fluency
Written Language (new in revised version)
Notes: The program address these five areas of literacy

## Slide 3: Participating Schools
Replacement Language Arts Core grades 4-8
Meeting A-G L.A. requirements for grades 9-10
An approved reading intervention for students in special education
Read 180 is approved by State of California as:

## Slide 4: Implementation Plan District Office
Prior to August 20:
Securing Teachers – currently interviewing
4 Full Time; 4 Part Time
Teacher Training in program
(Aug. 11-12 or 21-22)
Provide list of potential students to principals
Secure Materials for the site

## Slide 5: Continued
Get computer access for all sites (cloud based program)
Cohort groups set up in Illuminate for data
Administrator training for monitoring
Provide coaching schedule to sites

## Slide 6: Site Administrators:
Identify classroom available for 2 hours per day that has 5 computers for students
Schedule time for intervention and send to Debbie Daly
Based on list of students, determine priority list for assessment
Responsible for evaluation with support from sped program specialist.

## Slide 7: Teachers will:
8/20-9/5: Complete Fluency/SRI/SPI assessments for potential students
With administrator, identify students
Create student list in SAM (Read 180 data base)
9/8/14: Begin program
Develop smart goals for students
Collaborate with General Education Teachers

## Slide 8: Teachers cont.
Provide Language Arts Grade for students
Participate in Monthly Coaching provided by Scholastic
Monitor student performance weekly
Participate in monthly monitoring meetings at the district

## Slide 9
Elementary Entrance Process:
Notes: Information will be posted to web for your use. The spreadsheet from Ray will include Fluency Score and CST mirror as well as 2012-13 CST ELA proficiency level and CELDT score. The cut point included will be for Fluency and CST mirror.
You will need to add success maker data before creating your priority list

## Slide 10: Secondary Entrance Process
Notes: Fluency Score will be for 6th grade only. Secondary entrance criterion does not have a cut score.

## Slide 11: Elementary Exit Criterion
Notes: When students have completed the program, the expectation is they will continue to require Tier 2 support.

## Slide 12: Secondary Exit Criterion

## Slide 13: Tier 2 Intervention for students who exit Read180 that require additional assistance
Tier 2
Student Has Exited Read 180
Conduct Formative Assessment of Reading Needs
Create Reading Intervention Plan With Exit Criteria
Implement Plan
Continue Intervention or Exit Tier 2 Based On PM Data
Progress Monitor on 6 Week Intervals

## Slide 14
Questions